## Requirements
Assignment 2 Project Design Tasks | [6 empty] | Assignment 1 Project Requirements
Tasks: |  | Assigned To: | Completed By: |  |  |  | Task: | Assigned To: | Completed By:
Class Diagram |  | Bethel | Bethel |  |  |  | Introduction | Stockton | Stockton
Remove TicTacToe specific elements |  | John | John |  |  |  | Context Diagram | Bethel | Bethel
Create ALL new Classes for TWSG (without functionality) |  | Muhunga (Jules) | Muhunga (Jules) |  |  |  | User Interface (lobby and leaderboard) | Muhunga (Jules) | Muhunga (Jules)
Create ALL new Methods for TWSG (without functionality) |  | Rahat | Rahat |  |  |  | User Interface | Jules | Jules
Update Requirements (two person work) |  | Stockton | Stockton |  |  |  | System Requirements (write requirements) | John | John
[7 empty] | System Requirements (remaining parts of spreadsheet) | John | John
[7 empty] | Unknown List | Rahat | Rahat
[7 empty] | Review for consistency and completeness | Tran Dang | Tran
IMPLEMENTATION TODO LIST/TASK LIST ON SECOND SHEET LABELED IMPLEMENTATION TODO LIST (CHANGE SHEET AT THE BOTTOM OF THE EXCEL) |  |  |  | DEFECT LIST IS ON THIRD SHEET LABELED DEFECTS (CHANGE SHEET AT THE BOTTOM OF THE EXCEL)
SYSTEM REQUIREMENTS TABLE:
| F/NF: | Unique Id: | From: | Requirements Text: | Requirments Source: | Implamented By:
| F | UREQ001 |  | A letter grid is displayed to both players at the same time. (square 20x20 grid) | Product Description from pdf | initializeGrid()
| NF | UREQ002 |  | The letter grid will have words from the 'word list' embedded for players to find | Product Description from pdf | InitializeGridWithWords(); placeWord();
| NF | UREQ003 |  | A word list of randomly generated words will be provided to each user with the words that need to be found | Product Description from pdf | uniqueWords();
| F | UREQ004 | UREQ002 | Each Word will have a minimum of 3 letters | Product Description from pdf | uniqueWords();
| NF | UREQ005 | UREQ003 | Valid ENGLISH words from the word list are embedded into the grid | Product Description from pdf | uniqueWords();
| F | UREQ006 | UREQ002 | Words are embedded in either horizontally, diagonally, or vertically. Each can also be done in reverse order | Product Description from pdf | populateGridWithWords(); determineDirection();
| NF | UREQ007 | UREQ003 | The word list will have a total of 11 words | Group chosen length | WordBank.java
| NF | UREQ008 |  | A player can locate a word to gain score (1 score per point), the user 'wins' the word. | Product Description from pdf | handleButtonClick(); incrementPlayerScore();
| F | UREQ009 | UREQ008 | A player can locate a word by clicking once to select the start (changes letter color to player's color), and a second click at the words end (changes all letters colors to players color) | Product Description from pdf | handleButtonClick(); highlightRange();
| F | UREQ010 | UREQ008 | Only words from the 'word list' can be 'won' by the users | Product Description from pdf | handleButtonClick
|  | UREQ011 |  | Words will stay as the finder's color whenever a player locates them | Product Description from pdf | highlightRange();
| F | UREQ012 | UREQ011 | Words already found will no longer reward points | Product Description from pdf | sendHighlightedWord();
| F | UREQ013 | UREQ009 | The color changes for selected letters and words will be visible to both players | Product Description from pdf | sendHighlightedWord();
| NF | UREQ014 |  | There will be an 'existing users' array that is populated with the 'nicknames' that users have registered with | Project Requirements word doc (user interface section) | joinLobby();
| F | UREQ015 | UREQ014 | the 'nicknames' in the 'existing users' array will have a maximum length of 12 charactes | Project Requirements word doc (user interface section) | joinLobby();
| NF | UREQ016 |  | The website homepage will have a 'Enter Username' textbox where the user can enter their 'nickname' | Project Requirements word doc (user interface section) | html Page
| F | UREQ017 | UREQ016 | The website homepage will have a 'Register' button that will prompt the user to enter a 'nickname' to register | Project Requirements word doc (user interface section) | html Page
| F | UREQ018 | UREQ016 | If a Registering user enters an unused 'nickname', it is added to the list of 'existing usernames' | Project Requirements word doc (user interface section) | joinLobby();
| F | UREQ019 | UREQ016 | If a Registering user enters a 'nickname' already on the list of 'existing usernames', it will prompt the user that it is already taken | Project Requirements word doc (user interface section) | joinLobby();
| F | UREQ020 |  | The website homepage will have a 'Sign In' button that will prompt the user to enter a 'nickname' | Project Requirements word doc (user interface section) | html Page
| F | UREQ021 | UREQ020 | If a signing in user enters a 'nickname' saved in the list of existing users, they successfully login | Project Requirements word doc (user interface section) | joinLobby();
| F | UREQ022 | UREQ020 | If a signing in user enters a 'nickname' no in the list of existing users, they are prompted "user not found" | Project Requirements word doc (user interface section) | joinLobby();
| F | UREQ023 |  | Upon successful or sign in or registration, their entered 'nickname' will be added to the 'Player Waiting List' for all online users to see | Project Requirements word doc (user interface section) | joinLobby();
| F | UREQ024 |  | The game will only support two players at once per game, no more , no less | Product Description from pdf | startGame();
| F | UREQ025 |  | There will be a button labeled "play with 2 players" that will allow the user to play the game with another user | Product Description from pdf | html Page startGame();
| F | UREQ026 | UREQ024 | The game will start when there are two players that have hit the "play with 2 players" button | Product Description from pdf | startGame();
| F | UREQ027 |  | There will be a 'Player Waiting List' that displays all online users | Product Description from pdf | html Page
| F | UREQ028 |  | On game start, each player is given a color that will be indicated by the color of their 'nickname' | Product Description from pdf | startGame();
| F | UREQ029 |  | A player's score will be displayed next to their 'nickname' below the game | Project Requirements word doc (user interface section) | startGame();
| F | UREQ030 |  | The game will end when all words from the word list are found | Product Description from pdf | checkGameOver(); displayGameOver();
| F | UREQ031 |  | There will be a time limit of 1 minute displaying time until hint | Project Requirements word doc (user interface section) | startTimer();
| F | UREQ032 |  | Score updates for both players whenever a player scores a word | Project Requirements word doc (user interface section) | sendHighlightedWord();
| F | UREQ033 |  | The winner of the game is chosen by whoever has the higher score | Product Description from pdf | checkGameOver(); displayGameOver();
| F | UREQ034 |  | The winner is displayed with the message " 'username' wins!" | Project Requirements word doc (user interface section) | displayGameOver();
| F | UREQ035 | UREQ032 | If neither player has selected a start letter after 1 minute, a 'hint' is triggered wehere the system will prompt both players of the start letter of one of the remaing words from the word list | Product Description from pdf | startTimer(); highlight();
| F | UREQ036 | UREQ035 | The 'hint' will choose a word at random from the 'word list' and will be displayed next to time remaining | Project Requirements word doc (user interface section) | highlight();
| NF | UREQ037 |  | The homepage will have a section with text explaining the game rules | Project Requirements word doc (user interface section) | html Page
| F | UREQ038 |  | After a game finishes, players are allowed to either play again or return to the lobby | Project Requirements word doc (user interface section) | restartGame();
| F | UREQ039 | UREQ038 | If both players chooses 'play again', they will initiate a new game with the same players | Project Requirements word doc (user interface section) | restartGame();
| F | UREQ040 |  | If atleast one player chooses 'return to lobby', both players are returned to the waiting to play page | Project Requirements word doc (user interface section) | backToMenu();
| F | UREQ041 | UREQ016 | If a Registering user enters a 'nickname', and the input is either empty or contains invalid characters it will prompt the user that it is invalid | Project Requirements word doc (user interface section) | joinLobby();
| F | UREQ042 | UREQ016 | Usernames Submitted will ignore excess whitespace to prevent use of repeated names by adding whitespace | Project Requirements word doc (user interface section) | joinLobby();
| F | UREQ043 |  | If an environment variable VERSION exists, it will be displayed on the title of the webpage | Project Requirements word doc | index.html
| F | UREQ044 |  | if an environment variable WEBSOCKET_PORT exists, it will be used for the websockt port | Project Requirements word doc | app.java
| F | UREQ045 |  | The javascript/html page will connect to a websocket port that is 100 ports higher than the http port it has been loaded from | Project Requirements word doc | index.html
| F | UREQ046 |  | if an environment variable HTTP_PORT exists, it will be used for the http port | Project Requirements word doc | app.java

## Implementation Todo list
The Basic Frameworks for the HTML/CSS should be done first so we can see the functionality of our java code while testing/implementing |  |  |  |  | FOR ALL OF THESE JAVA TODOS MAKE SURE TO LINK THEM TO THE HTML FOR LIVE TESTING
| Class Implemented | Picked Up By: | Implemented By | Implement Date |  | Class Implemented | Picked Up by: | Implemented By: | Implement Date
Webpage TODOs |  |  |  |  | Functionality TODOs
HTML Game Page: |  |  |  |  | Grid:
Display 50x50 Grid | InitializeGrid(); | John & Stockton | John & Stockton | 2024-04-15 | Initialize Grid (50x50) | InitializeGrid(); | stockton | stockton | 2024-04-13
Player Names corresponding with color | startGame(); | John | John | 2024-04-13 | Generate Random Words with length 3 letters atleast | uniqueWords(); | stockton | stockton | 2024-04-13
Score Box with color | styles.css | Bethel | Bethel | 2024-04-29 | Populate Grid with words in random orientations | populateGridWithWords(); determineDirection(); | stockton | stockton | 2024-04-13
Word List(used words in uniqueWords set) | onMessage, uniqueWords(); | John & Stockton | John & Stockton | 2024-04-15 | Fill Empty Grid Slots with Random Letters | uniqueWords(); | stockton | stockton | 2024-04-13
Timer for Hint | startTimer(); | Stockton | Stockton | 2024-04-16 | Connect Java Grid to HTML game page | onMessage(index.html) | stockton | stockton | 2024-04-15
Cosmetic(optional if we have time) | styles.css | Bethel | Bethel | 2024-04-29
HTML Login Page: |  |  |  |  | Player:
Login box with submit button | index.html, joinLobby(); | jules (muhunga) & John | jules (muhunga) & John | 2024-04-28 | send username to java from js/html | joinLobby(); | John | John | 2024-04-23
Basic Logo (optional if we have time) |  |  |  |  | Check player username on login attempt | joinLobby(); | John | John | 2024-04-26
Cosmetic (optional if we have time) | styles.css | Bethel | Bethel | 2024-04-29 | Generates valid errors for logins when needed | joinLobby(); | Bethel | Bethel | 2024-04-21
[5 empty] | Add waiting players and clear username to exit | window.addListenerEvent(); | Bethel | Bethel | 2024-04-21
HTML Lobby Page: |  |  |  |  | add the player to the list of waiting players | joinLobby(); | jules (mahunga) | jules (mahunga) | 2024-04-14
Player Display showing all players at lobby screen | joinLobby(); | Rahat | John | 2024-04-28 | Start Game:
Game Waiting Screen | index.html | Rahat | John | 2024-05-01 | Assign players a color on game start | startGame(); | John | John | 2024-04-29
Cosmetic(optional if we have time) | styles.css | Bethel | Bethel | 2024-04-29 | Timer counting down until hint | startTimer(); | stockton | stockton | 2024-04-16
[5 empty] | Modify to start game on press, rather than on page load | startGame(); | John | John | 2024-04-29
MISC |  |  |  |  | Score Tracker
connect to vps |  | John | John | 2024-04-13 | Gameplay:
[5 empty] | Valid Word Checker |  | jules (muhunga) | jules (muhunga) | 4/25/024
Update Requirements Page |  | John | John | 2024-04-30 | Valid Move Checker |  | jules (muhunga) | jules (muhunga) | 2024-04-25
Unit Tests (game.java) |  | Stockton | Stockton | 2024-05-01 | Calculate Score |  | jules (muhunga) | jules (muhunga) | 2024-04-27
Unit Tests (App.java) |  |  |  |  | End Game and Display winner and final scores |  | jules (muhunga) | jules (muhunga) | 2024-04-27
[5 empty] | Display Selected Letters/Words |  | jules (mahunga) | jules (mahunga) | 2024-04-27
[5 empty] | Hint letter Highlights |  | stockton | stockton | 2024-04-16
[5 empty] | Game Color Communication | on message (index.html) | john | john | 2024-05-01

## Defects
Defect No. | Defect Description | Date Resolved
1 | Username was taking just whitespace | 2024-04-26
2 | Duplicate usernames by adding whitespace | 2024-04-26
3 | waiting player list sometimes displayed duplicates | 2024-04-29
4 | first letter select not resetting color on second invalid button choice | 2024-04-29
5 | Clearing Hint highlight removes player's color on the button | Could not fix by turn in date
6 | Highlights selected word withplayers Color no matter if its a valid word or not | 2024-05-01
7 | Endgame does not remove usernames from waiting player list and leaves them in there forever | 2024-05-01
8 | Words can be scored more than once | 2024-04-29
9 | Timer stats before 2 players are found, so this leads to asynchronous hint countdowns | 2024-05-01
10 | color reset on invalid selection resets button background to white no matter what it was before | Could not fix by turn in date
11 | Game interface displays player1 and player2 and not usernames | 2024-05-01
12 | When less than 10 items in word list, displayed wordlist repeats last word | Could not fix by turn in date
13 | No rematch function | Could not fix by turn in date
14 | Game does not close when a player closes the page | Could not fix by turn in date
15 | Page only displays 10 out of the 11 words at the start of the game | Could not fix by turn in date
16 | Does not have page explaining the game or game rules | Could not fix by turn in date
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99